## Sheet1
| Task | Time | Dependencies
T1 | Developed API | 10 Days
T2 | Design Landing Page | 4 Days
T3 | Design Mobile App | 5 Days
T4 | Design Database | 2 Days
T5 | Integrate API with Database | 7 Days | T1, T4 (M1)
T6 | Design Admin Page | 4 Days
T7 | Integrate Website with API | 6 Days | T5, T6 (M2)
T8 | Integrate Mobile with API | 4 Days | T5, T3 (M3)
T9 | Developed Routing Algorithm | 3 Days | T5
T10 | Embed Google Maps | 5 Days | T7, T8, T9 (M4)